## Worksheet
Activity area | Lesson learned | Suggestion for improvement
Quality | Institutions have various structures in place for documenting concern data. Those structures will not be suitable for gathering all the study-particular data. | On-site source documentation must be customized, and a well-designed study should be established before the study starts.
Capacity building | When it comes to capacity building, having a space to share skills and knowledge can be more beneficial. | Organize training sessions across many locations and hire site representatives as trainers. The sponsoring enterprise’s role is to organize logistics and provide global coordination.
Monitoring | Effective collaboration between site monitors and site workers is necessary to ensure high-quality clinical testing. | Regular collaborative monitoring is essential to guide the study process and facilitate on-site engagement.
Audit | Expert audits have significantly improved the quality and accountability of research conducted. | Audits must be scheduled so that each research site is involved or included in the process at least once.
Vaccine management | Logistics support must be identified to reduce risks with vaccine distribution. | Simulating onsite deliveries prior to vaccine testing can significantly reduce study timelines.